## Daily Status Report
SMARTKISAN PROJECT - DAILY STATUS REPORT (DSR)
AI weed-detection model training - 2026-08-10. GOG and YOG baselines trained and measured; accuracy improvement in progress.
Date | Task Category | Detailed Task Description | Deliverables / Artifacts | Status | Remarks & Notes
2026-08-10 | ML - Green-on-Green (GOG) | Built and trained the Green-on-Green weed classifier. MobileNetV2 backbone at 224px, two-phase schedule (frozen head, then fine-tune of the last 30 layers), trained on the DeepWeeds dataset (17,509 images, 9 classes). Applied inverse-frequency class weights because the set is 52% 'Negative'; without them the model scores 52% by predicting Negative for everything. | gog_model.tflite (2.4 MB), class_labels.json, train_weed_model.py | Completed | Validation accuracy 77.6%. Per-class recall: Parkinsonia 97.1%, Rubber vine 92.5%, Siam weed 92.5%, Parthenium 90.7%, Lantana 89.6%, Prickly acacia 87.7%, Snake weed 80.3%, Chinee apple 76.0%, Negative 67.9%. The headline figure is held down by Negative, which is the majority class; every weed species is between 76% and 97%.
2026-08-10 | ML - Yellow-on-Green (YOG) | Built and trained the Yellow-on-Green crop-stress classifier from the PlantVillage split already held locally, regrouped into three classes: healthy, chlorosis and other_stress. 'chlorosis' groups the diseases whose dominant sign is yellowing or mottling (citrus greening, tomato yellow leaf curl and mosaic viruses, Esca, rust flecking) rather than discrete lesions. | yog_model.tflite (2.4 MB), class_labels.json | Completed | Validation accuracy 99.2%. Per-class recall: healthy 99.8%, chlorosis 99.4%, other_stress 98.6%. Caveat: PlantVillage is captured under controlled conditions with uniform backgrounds, so this figure will not transfer directly to field photographs. Field validation required before it is treated as production accuracy.
2026-08-10 | ML - Data sourcing (accuracy improvement) | Identified that DeepWeeds is rangeland imagery - individual weeds against soil and scrub, effectively Green-on-Brown - so it does not teach the model to separate weed from crop when both are green, which is what GOG actually requires. Sourced CoFly-WeedDB (Zenodo, CC-BY-4.0): 201 UAV frames over a cotton field with per-pixel masks. Wrote prepare_cofly.py to convert that segmentation into 3,399 classification patches via centre-weighted tiling. | prepare_cofly.py, 3,399 in-crop patches, --task cofly | In Progress | This is the main lever for improving GOG accuracy in real conditions. Next step is fine-tuning the DeepWeeds backbone on these in-crop patches. Known limitation: field_bindweed has only 50 patches from 14 source frames, which is too few to learn the species rather than memorise those scenes.
2026-08-10 | ML - Infrastructure | Made training resumable after two full runs were killed mid-epoch and lost all progress. Root cause was host memory, not the code: the machine has 15.2 GB with under 1 GB typically free, and TensorFlow was terminated on every allocation spike. Model and a state cursor are now written after every epoch, a re-run continues from that cursor, and a wrapper script restarts automatically. Also added per-class recall reporting. | run_training.sh, resumable checkpointing, per-class metrics | Completed | Memory footprint reduced from multiple GB to ~315 MB (batch 32 to 8, bounded shuffle/prefetch buffers). A kill now costs one epoch instead of the whole run. Per-class reporting was added because a single accuracy figure can hide a class the model never gets right, which matters when the output drives a spray decision.