## Daily Status Report
SMARTKISAN PROJECT - DAILY STATUS REPORT (DSR)
Defect resolution and stability fixes - 2026-08-12. Authentication, account deletion, notifications, real-time connectivity and data integrity.
Date | Task Category | Detailed Task Description | Deliverables / Artifacts | Status | Remarks & Notes
2026-08-11 | Bug Fix - Notifications | Fixed the notification feature never displaying anything. The screens, slice and storage helper were all present but nothing was connected: no code dispatched addNotification or setNotifications, the storage helper was never imported, and the socket client was never connected, so the server's real-time events had no listener. Wired MQTT alerts into the notification store and connected the socket on login. | App.js, src/services/socketService.js | Fixed | The Home bell also rendered its unread dot unconditionally, showing an alert indicator whether or not anything was unread. It now reflects the real count and opens the notification list. Notification history persists across app restarts.
2026-08-11 | Bug Fix - Real-Time / Config | Fixed the socket client pointing at a service that does not exist. It targeted a hostname returning 404, used an /api path where Socket.IO does not attach, and opened a connection at import time before any user had signed in. Now derives the server origin from the configured API URL so the two cannot drift, and connects explicitly after login. | src/services/socketService.js, src/services/backendApi.js | Fixed | Verified against the live deployment: Socket.IO handshake returns 200 and the existing REST routes continue to authenticate correctly.
2026-08-11 | Issue Resolution - Data Integrity | Removed code paths that presented generated values as real measurements. Disease detection returned a randomly chosen diagnosis with a confidence score and a chemical treatment whenever the model was unreachable, indistinguishable from a genuine result. Soil substituted placeholder moisture, pH and NPK readings when no sensor had reported. Both now report the failure or show an empty state. | src/services/api.js, ScanResultScreen.js | Fixed | Highest-severity item of the set: acting on an invented diagnosis means applying the wrong chemical, and invented soil readings drive irrigation and fertiliser decisions. A scan that cannot run now fails with the reason instead of guessing.
2026-08-11 | Bug Fix - Backend Stability | Fixed the API rejecting all traffic behind the hosting proxy. The rate limiter refuses any request carrying an X-Forwarded-For header unless proxy trust is configured, which behind the platform proxy is every request. Configured trust for exactly one hop, so clients cannot spoof the header to bypass rate limiting. | backend/src/server.js | Fixed | Would have failed on the first request after deployment. Verified with a simulated proxy header locally and with rapid repeat calls against the live service.