## Daily Status Report
SMARTKISAN PROJECT - DAILY STATUS REPORT (DSR)
Backend cold-start mitigation and code cleanup - 2026-08-26.
Date | Task Category | Detailed Task Description | Deliverables / Artifacts | Status | Remarks & Notes
2026-08-26 | Backend - Cold Start Fix | Diagnosed and mitigated the hosting platform's idle sleep. The free tier suspends the service after roughly 15 minutes without traffic, and the next request has to wait for it to restart. Nothing in the app woke the server before it was needed, so the whole restart landed on the user's first action - which was the sign-in itself. | src/features/auth/screens/LoginScreen.js | Fixed | Measured 22.5s on a cold call against 0.26s warm. The login screen now pings the API when it opens, so the restart overlaps the seconds the user spends on the Google account picker. Fire-and-forget, so it never blocks the form, and it benefits email sign-in equally.
2026-08-26 | Backend - Request Timeout | Increased the API request budget and added a retry. The client allowed 15 seconds per call, which is less than a cold start takes, so any request that arrived while the service was waking was abandoned mid-restart and surfaced as a connection failure. | src/services/backendApi.js | Fixed | Now three attempts with an explicit 30s window each. HTTP errors are excluded from the retry - a wrong password should fail immediately rather than being retried against a verdict already received.
2026-08-26 | ML Service - Cold Start Fix | Applied the same treatment to the plant disease model, which is hosted separately and sleeps on the same basis. The scan screen now warms the model when it opens, so it is ready by the time the user has framed a photograph. | src/services/api.js, DiseaseDetectionHomeScreen.js | Fixed | Measured 9.1s cold against 1.15s warm. Previously the timeout expired during the wake-up and the app fell back to placeholder output; that fallback has since been removed entirely.
2026-08-26 | Code Cleanup - Dead Feature Code | Removed the simulated camera-rig implementation from the field monitor screen after it was replaced with real on-device inference. The old implementation animated a scanning sequence and generated its results locally rather than from any model. | WeedDetectionHomeScreen.js | Completed | 1,420 lines reduced to 425. Removing it also made three dependencies unreachable - a graphics library, a slider control and a haptics module - all of which existed only for that screen.
2026-08-26 | Code Cleanup - Dependencies & Package Size | Removed the three orphaned dependencies and trimmed the build to the two processor architectures used by real phones. The package was shipping two further architectures that exist only for emulators. | package.json, scripts/build-apk.sh | Completed | Package reduced from 134 MB to 71 MB. The architecture setting lives in a generated folder that is recreated whenever a native dependency changes, so an earlier fix had already been silently lost once; it is now passed by a build script that survives regeneration.
2026-08-26 | Code Cleanup - Unused Imports & Strings | Removed sample-data imports left behind when those screens moved onto the real API, and replaced the translation strings for the field monitor, which still described the removed simulation rather than the current screen. | src/services/api.js, src/i18n/locales/en.js | Completed | Leaving unused sample-data imports in place makes it easy to reintroduce a fallback that silently replaces real data, which is what several earlier defects turned out to be.
2026-08-26 | Build Cleanup - Upload Size | Excluded machine-learning datasets, the backend and local documentation from the cloud build upload. The archive had reached 423 MB and the upload was failing partway through; application source is only a few MB of that. | .easignore | Completed | The exclusion file replaces the normal ignore rules rather than adding to them, so it repeats the standard exclusions as well.