## Daily Status Report
SMARTKISAN PROJECT - DAILY STATUS REPORT (DSR)
Defect resolution following the QA testing report - 2026-08-28 and 2026-08-29.
Date | Task Category | Detailed Task Description | Deliverables / Artifacts | Status | Hours Spent | Remarks & Notes
2026-08-28 | Backend - Reliability | Reviewed the server for reliability gaps and fixed five. The health check the hosting platform polls reported healthy without testing anything, so an instance that had lost its database stayed in service while every request failed. It now queries the database and reports unhealthy with the reason when that fails. | backend/src/server.js | Fixed |  | This is the one situation the health check exists to catch, and it was the one situation it could not detect.
2026-08-28 | Backend - Deploy Safety | Added an orderly shutdown. The hosting platform signals the server before every deployment and before idling it; with no handler, requests in progress were cut off mid-response and database connections were abandoned rather than closed. The server now stops accepting new work, lets current requests finish, and closes its connections. | backend/src/server.js | Fixed |  | Abandoned connections matter on the current hosting plan because the number of simultaneous connections is capped.
2026-08-28 | Backend - Security | Tightened the limit on login attempts. Sign-in shared the general allowance of 100 requests a minute, which is 100 password guesses a minute. Credential endpoints are now limited to 10 attempts per 15 minutes, and a successful sign-in does not consume the allowance. | backend/src/server.js | Fixed |  | Counted per account rather than per network address. Indian mobile networks place many customers behind a shared address, so a per-address limit would let ten bad attempts lock out everyone on that network. Verified: the targeted account is blocked while another user on the same address signs in normally.
2026-08-28 | Backend - Input Handling | Added checks on submitted data. Values were passed straight to the database, so a letter where a number was expected came back as a generic server error that told the user nothing and filled the logs with database errors that were really typing mistakes. Invalid input now returns a message naming the field. | backend/src/middleware/validate.js | Fixed |  | Applied to field creation so far; the remaining write operations still need the same treatment.
2026-08-28 | Backend - Automated Verification | Built an automated check that exercises the API the way the app does: sign up, sign in, farm setup, adding and editing records, sensor readings, confirming one account cannot read another's data, and account deletion. Reports pass or fail for each step and can be run with a single command. | backend/scripts/e2eCheck.js (npm run e2e) | Completed |  | 40 of 40 checks passing. It creates temporary accounts and removes them afterwards, so it is safe to run against the live service. This also tested account deletion for the first time - the code existed but had never been run against real data. Confirmed working.
2026-08-29 | Defect Fix - Data Not Saving | Fixed pumps and soil readings not being stored. Both features were still using sample data: adding a pump produced a temporary entry that was never sent to the server, so it appeared in the list and was gone after restarting the app, and adding a soil reading did nothing at all. Every account also saw the same sample pumps. | src/services/api.js | Fixed |  | Raised by QA as three separate items. The server side and the connecting code both already existed; these two features had simply been missed when the others were moved across.
2026-08-29 | Defect Fix - AI Field Monitor | Fixed the weed scan producing no result. The photograph was captured and analysed, but the result was read from the analysis engine in the wrong format, which produced an empty answer instead of an error. The screen therefore had nothing to display. | src/services/weedInference.js | Fixed |  | The model itself was never at fault. Confirmed by running the app's exact processing sequence against the reference images: 12 of 12 correct at 98-100% confidence. This defect could only be found by running the app on a phone, so the QA round is what surfaced it.
2026-08-29 | Defect Fix - Registration | Added format checks on the registration form. Only presence was checked, so an entry like 'abc' was accepted as an email address and any sequence of digits as a phone number. The email address is where a password reset would be sent, so an invalid one is only discovered when it is needed. | src/features/auth/screens/RegisterScreen.js | Fixed |  | Phone rule matches Indian mobile numbers and accepts the +91, leading zero, spaces and dashes people actually type.
2026-08-29 | Defect Fix - Sign-in and Weather | Two smaller corrections. An error message from one sign-in method stayed on screen after switching to another, so a failed code was still displayed while the user was on the email form. Separately, the weather screen showed a default location instead of the farm's own: the location is saved with the farm, but nothing restored it after a reinstall or on a second device. | LoginScreen.js, App.js | Fixed |  | The pump form also always read 'Edit' because one screen serves both adding and editing; it now reflects which is happening.
2026-08-29 | Build & Handover | Produced a new build containing all of the above and confirmed each fix is present in the packaged application. Prepared a reference image set so the AI field monitor can be verified against images with known answers. | SmartKisan APK (71 MB), weedDetection/test_pack | Completed |  | Three items from the QA report are not defects: analytics, crop suitability and farm management have no server behind them yet and show the same sample figures to everyone, which is a decision to build or label rather than something to repair. Phone and username sign-in need a messaging provider before they can work.