## DSR
SmartKisan - Daily Status Report
Period: 31 August - 2 September 2026 (following the 28-29 August report)
Date | Task Category | Detailed Task Description | Deliverables / Artifacts | Status | Hours Spent | Remarks & Notes
2026-08-31 | Onboarding - Farm Location | Onboarding never asked where the farm is, so the app fell back to a default set of coordinates. The weather screens and the farm map widget both read from that, which is why testers saw weather for somewhere other than their farm. Setup now collects the location and the app applies it on every launch. | OnboardingScreen.js, settingsSlice.js, App.js | Fixed |  | Addresses TC-014. The location is stored on the farm profile, so it survives reinstalling the app.
2026-08-31 | Authentication - One-Time Codes | Built one-time codes on the server for three flows that had no implementation: signing in without a password, confirming an email address at sign-up, and resetting a forgotten password. Codes are stored hashed, expire in ten minutes, allow five attempts and can be used once. | otpService.js, mailService.js, auth.js, addAuthCodesSchema.js | Completed |  | A request answers identically whether or not the address is registered, so the endpoint cannot be used to discover which emails have accounts.
2026-08-31 | Login - Replacing Dead Tabs | The Phone and Username login tabs could not work: there was no SMS provider and no username lookup, so both reported themselves unavailable after the user had filled the form. Replaced with email code sign-in, which gives a genuine second way into an account. | LoginScreen.js, CodeLoginForm.js, LoginTabBar.js | Fixed |  | Addresses TC-007 and TC-008. Also fixes the reported problem of an error from one tab staying on screen after switching to another.
2026-08-31 | Stability - Expo Go Crash | The weed detection model loader was imported at start-up. It is a native module, so on Expo Go the app crashed before reaching the login screen. The loader is now resolved only when a scan is run. | weedInference.js | Fixed |  | Made the app testable in Expo Go again; the model itself still needs a development build.
2026-08-31 | Stability - Blank Screen at Launch | While the session was being restored the app rendered nothing. On the free hosting tier the server can take about fifty seconds to wake, so a cold start showed a white screen for the whole period and looked like a hang. Replaced with a loading indicator. | App.js, RootNavigator.js | Fixed |  | Defect introduced by our own earlier change; found in testing.
2026-08-31 | Deployment - Mail Configuration | Declared the mail credentials in the deployment blueprint. The local environment file is not committed, so the hosted service had none of them and code delivery failed there while working locally. | render.yaml, .env.example | Completed |  | Secrets remain outside the repository; the blueprint only declares that they are required.
2026-09-01 | Email Delivery - Host Restriction | Sign-in codes hung for over two minutes on the hosted service while the health check answered in under a second. The cause is that the host blocks outbound SMTP to prevent spam, and the connection stalls rather than failing. Moved delivery to an HTTPS mail API, which is unaffected, keeping SMTP for local development. | mailService.js, render.yaml | Fixed |  | Reported as the code request spinning forever and then saying the request had been cancelled. Connection timeouts were also added so a future block fails quickly instead of hanging.
2026-09-01 | Authentication - Phone Codes | Extended one-time codes to phone numbers, since many farmers do not have an email address. One code path serves both channels; only delivery differs. Numbers are normalised so that +91, a leading zero and spacing all resolve to the same account. | smsService.js, otpService.js, addPhoneAuthSchema.js | Built - Not Live |  | Cannot deliver until DLT registration with TRAI is complete. No provider will send to an Indian number before then. This is a business registration, not development work.
2026-09-01 | Profile - Update Defect | The profile screen read the farm name and location from the user record, which holds only id, name and email, so both fields opened blank however much had been entered during setup. They belong to the farm profile and are now read from there. Saving also did nothing at all: the update was applied to local state and discarded on restart. Added the missing server endpoint and the missing validation. | UserProfileScreen.js, authSlice.js, api.js, auth.js (PUT /auth/me) | Fixed |  | Addresses TC-019. The reported symptom was the blank fields; the silent failure to save was found while fixing it. Phone numbers are now unique across accounts.
2026-09-02 | Authentication - Password Reset | Added the password reset screen. The server could already issue and verify reset codes and the app had the logic wired to them, but nothing reached it: the 'Forgot password?' link on the login form had no action attached. A user who forgot their password had no way back into their account. | ForgotPasswordScreen.js, AuthStack.js, EmailLoginForm.js | Fixed |  | Verified by an automated check covering the refusals, the reset itself, the old password ceasing to work and a code not being reusable. Thirteen checks, all passing.
2026-09-02 | Pumps - Queries Against Missing Columns | Four database queries named columns that do not exist, so each failed every time it ran. Adding a pump always returned an error, which is why a new pump appeared in the list and was gone after restarting. Editing a pump had the same fault. Switching a pump on or off returned an error after having already switched it. The real-time handler failed at its first query. | pumps.js, mqttService.js | Fixed |  | Addresses TC-012. Not one pump run had ever been recorded as a result: the history table was empty. History writes were also moved out of the path that can fail the request, since losing a log line must not fail the action it describes.
2026-09-02 | Dashboard - Invented Figures | The Today card multiplied the number of running pumps by fixed constants to produce run hours, water used and power used. This is why every login showed identical numbers. With runs now recorded, the figures are derived from real data: litres from each pump's flow rate and kilowatt-hours from its horsepower, against the time it actually ran, over the farm's own day rather than the server's. | pumps.js (GET /pumps/summary/today), HomeScreen.js, pumpsSlice.js | Fixed |  | Addresses TC-010. The card shows a dash rather than a zero when nothing has run, so it never states a total it does not have.
2026-09-02 | Verification - Automated API Check | Extended the end-to-end check to cover the profile update, the full pump chain (create a pump, run it, confirm the run was recorded and the derived totals are arithmetically correct) and the new task endpoints. | backend/scripts/e2eCheck.js, backend/scripts/checkPasswordReset.js | Completed |  | 67 of 67 checks passing. The pump defects above were found by writing this, not by reading the code.
2026-09-02 | Crop Suitability - Sample Soil | The screen called the recommendation engine with no arguments, which fell back to a fixed sample soil profile and sample climate. Every farmer saw recommendations computed from someone else's soil, under the heading 'Your Soil Profile'. It now uses the farm's own recorded reading, and shows nothing when there is none. | api.js, cropRecommendSlice.js | Fixed |  | Addresses TC-015. Advising a crop from invented nitrogen is worse than advising nothing, so an absent reading is stated rather than filled in. Entering values by hand still works as before.
2026-09-02 | Weather - Sample Data and Fixed History | Weather fell back to a fixed sample forecast whenever the farm had no location set, and the historical screen used sample data unconditionally - it showed the same week of December 2024 to every user, forever, because nothing had ever been written to fetch real history. Implemented real historical weather and made every weather call fetch a genuine observation. | weather.js, api.js, weatherSlice.js | Fixed |  | No API key is needed: the app already uses Open-Meteo, which is free and keyless, so there was never a reason to invent this. With no farm location set it now fetches real weather for the default location, which is what the on-screen banner already told the user was happening.
2026-09-02 | Disease Detection - Unreliable Diagnoses | The classifier has no 'not a plant leaf' category, so it always names some disease. A photo of a weed came back as tomato early blight at 46% confidence together with a fungicide to spray, presented exactly like a real diagnosis. Results below 60% confidence now ask for a clearer photo instead of naming a disease and a treatment. | api.js (scanImage) | Fixed |  | Found while investigating TC-016. A farmer acting on a coin-flip diagnosis buys fungicide and sprays a plant that did not need it, so an unreliable answer has a real cost.
2026-09-02 | Farm Management - No Storage | The farm management screen had nothing behind it: a fixed sample list, an Add button that opened an alert saying nothing, and a completion state that lived only in memory. Added the table and endpoints, a form to add a task, and made tapping a task complete it. | farm_tasks table, farmTasks.js, AddTaskModal.js, farmSlice.js | Fixed |  | Addresses TC-020. New work rather than a defect fix, as the feature had never been connected to anything. Growth trends need a season of recorded crop measurements that nothing collects yet, so that chart is empty rather than showing a fabricated curve.
Open Items
Reference | Item | Blocked On / Next Step
TC-016 | Disease detection reported as showing a rejection | The model service was tested directly and works: it returns a correct prediction in about a second once warm, and eleven seconds from cold, well inside the app's timeout. Still awaiting the exact error text from the testing team to identify what they saw.
Phone sign-in | Codes cannot be delivered to Indian numbers | Requires DLT registration with TRAI before any provider will send. Business registration, not development.
Field monitor | Weed detection needs a development build | The model is a native module and cannot run in Expo Go, so it can only be confirmed on an installed build.