## DSR
SmartKisan - Daily Status Report
Tuesday 15 - Wednesday 16 September 2026 (following the 10-14 September report)
Date | Task Category | Detailed Task Description | Deliverables / Artifacts | Status
2026-09-15 | Weed Model - The Real Test | The disease model got much better last week once real field photographs were added to its training. I set out to do the same for the weed model, using weed collections from India. On the usual tests it looked like a big win - about thirteen points. So I tested it properly, on 540 photographs taken by ordinary people on their phones rather than by a research project. Every version scored between 80 and 83 percent. The old one, the new ones, all the same. | fetch_wild_test.py, evaluate_weed_type_only.py, train_weed_model.py | Completed
2026-09-15 | Disease App - Wrongly Saying a Plant is Healthy | The app refuses to answer when it is not confident, so it does not name a disease off a guess. But that check only applied when it named a disease. If it said the plant was healthy, it went straight through however unsure it was. That is the wrong way round: a wrong disease costs one spray, a wrong all-clear can cost the crop, because the farmer then does nothing. The check now applies both ways. | src/services/api.js | Fixed
2026-09-15 | Disease App - Refusals Looked Like Failures | When the app declined to answer an unclear photograph, it showed "Scan Failed" - the same message as when it could not reach the server at all. So the safety check doing its job looked like the feature being broken, which is what the testing team reported. It now says "Try another photo" and explains what to change. | DiseaseDetectionHomeScreen.js, diseaseDetectionSlice.js | Fixed
2026-09-15 | Disease Service - Guard Against a Bad Upload | A model and its list of disease names have to be replaced together. In my working folder they were not, for a day. Uploading it in that state would have looked completely normal - the server would start, every request would succeed - while every photograph was matched to the wrong name and the wrong chemical. The service now refuses to start if the model and the name list disagree. | plantDetection/huggingface/app.py | Fixed
2026-09-16 | Disease Service - Correcting My Own Note | I had recorded that the new disease model was prepared but not yet live. It is live, and has been since Monday. I had been reading my working folder as though it were the running service; the service is ahead of it. The note in the repository now says so. | plantDetection/huggingface/README.md | Corrected
Open Items
Area | Item | What it needs
Weed model | Retraining on the 36,000 real photographs | Ready to start. Roughly a day: a few hours to download, then an overnight training run.
Weed model | Stop the model guessing whether the plant is the crop | Worth about three points, no retraining needed. The app should answer this from the farmer's own crop instead.