## DSR
SmartKisan - Daily Status Report
28 - 30 September 2026
Date | Task | What was done | Status
2026-09-28 | Harvest records | Built the screen and the storage to record what actually comes off each field - quantity, area, quality and what was expected. Handles quintals, kilograms, tonnes and maunds over acres, bigha or hectares. | Completed
2026-09-28 | Yield prediction | Now works, because harvests are recorded. It shows the farmer's own average yield per acre over the area planted. It was showing the same invented figures to everyone before. | Completed
2026-09-28 | Harvest report | The harvest performance report shows real figures. It used to show 91.7% efficiency to every farmer. | Completed
2026-09-29 | Weather forecast | Days six to fourteen of the forecast were being made up - the first five days repeated with random changes. They now come from a service that actually forecasts fourteen days. | Fixed
2026-09-29 | Weather advice | Added what the forecast means for the week's work: which days are fit to spray and why not on the others, plus heat, frost and heavy rain warnings with the day named. | Completed
2026-09-29 | Weed detection | Stopped the model guessing whether a plant is the crop - it gets that right only 23 times in 100. The app answers it from the crop the farmer entered instead. Worth about three points. | Fixed
2026-09-29 | Report screens | Three report screens had their figures written into the code, so the real data from the server never reached the farmer. Connected them properly. | Fixed
2026-09-30 | App reads aloud | The app now reads its advice out in the farmer's own language - the disease result, the weed result, farm observations and weather warnings. This matters for farmers who cannot read comfortably. | Completed
2026-09-30 | App listens | The farmer can speak to move around the app, in Hindi, Punjabi and English. It only navigates and never saves anything, so a misheard word cannot get written into a record. | Completed
2026-09-30 | Hindi and Punjabi | Translated the new screens into Hindi and Punjabi rather than leaving them in English. | Completed
2026-09-30 | Testing and build | Built a new APK and checked the voice commands with an automated test - 43 spoken phrases across all three languages. Updated the testing manual, the feature list and the gap analysis. | Completed
Notes
A new APK is ready for the testing team. The voice features need the installed APK - they cannot run in Expo Go.
The microphone works in Hindi, Punjabi and English only. The phone's recogniser handles the other seven languages poorly, so it is hidden there rather than offered and disappointing.
The Hindi and Punjabi wording should be read by a native speaker before release.