## DSR
SmartKisan - Daily Status Report
Thursday, 3 September 2026 (following the 31 Aug - 2 Sep report)
Date | Task Category | Detailed Task Description | Deliverables / Artifacts | Status | Hours Spent | Remarks & Notes
2026-09-03 | AI Models - Measurement | Built test harnesses for both AI features. Until now the only figure either model had was its training accuracy, which is measured on images from the same collection it learned from and reports memorisation rather than usefulness. Both are now scored against photographs taken elsewhere, in real conditions. | evaluate_weed_model.py, evaluate_disease_model.py, evaluate_field_model.py | Completed |  | This is the groundwork for every result below. Neither model could previously be judged before release.
2026-09-03 | Disease Detection - Field Accuracy | The disease model had only ever seen laboratory photographs: one detached leaf on a plain background under even light. The app only ever receives photographs taken in a field. Retrained it on field imagery while retaining what it already knew. | finetune_field.py, field_model.tflite | Ready to Deploy |  | Correct diagnoses rose from 28% to 58% on real field photographs. More importantly, the old model called 47% of HEALTHY plants diseased, recommending a fungicide that was not needed; that is now 8%. Laboratory accuracy was barely affected, 99% to 97%.
2026-09-03 | Disease Detection - Safety Threshold | Raised the confidence level below which the app declines to name a disease, from 60% to 70%, based on measurement across the same test set. At 60% the app answers 56% of scans with 75% of those correct; at 70% it answers 47% with 84% correct. | src/services/api.js | Fixed |  | Nearly halves the wrong diagnoses a farmer is shown. An unanswered scan costs someone another photograph; a wrong one costs them a fungicide and a sprayed plant that did not need it.
2026-09-03 | Weed Detection - Training Experiments | Tested whether adding two further public datasets would improve weed identification, as requested. Both were trained and measured. Both made the model worse on real photographs and neither is used. | train_weed_model.py (--task combined) | Investigated - Not Adopted |  | Accuracy on unfamiliar photographs fell from 87% to 73% with one dataset added and to 53% with both. The added imagery was Australian rangeland and drone footage - neither resembles a farmer's phone photograph. The existing model remains in the app and is the better one.
2026-09-03 | Weed Detection - Test Coverage | The weed model was being judged on 15 photographs, so a difference of two images looked like a meaningful result. Added two further test sets already available on disk, giving 1,284 images the model has never seen. | evaluate_weed_model.py | Completed |  | The earlier conclusion held on the larger sample and the margin widened. It also revealed a weakness the small set could not: grass weeds are identified correctly only 13% of the time in unfamiliar conditions. Grass versus broadleaf decides which herbicide to buy, so this is the priority for the next round of work.
2026-09-03 | Weed Detection - Incorrect Information Shown | The note displayed to the farmer described a model that is not in the app, naming datasets replaced in August. Corrected to describe what actually runs, including that grass weeds are its weakest class. | WeedDetectionHomeScreen.js, weedInference.js | Fixed |  | Telling someone the wrong thing about how a spraying decision was reached is worse than telling them nothing.
2026-09-03 | Model Tuning - Three Further Attempts | Tried three further techniques to improve the disease model beyond 58%: a larger training run, averaging over multiple views of each photograph, and weighting rare diseases more heavily. All three were measured and none is adopted. | finetune_field.py | Investigated - Not Adopted |  | Each result is recorded in the code beside the setting it concerns so the work is not repeated. The conclusion is that the remaining weakness is a shortage of training photographs for specific diseases, not a shortage of tuning.
Open Items
Reference | Item | Blocked On / Next Step
Disease model | Trained and verified, not yet live | Needs a HuggingFace access token to upload. Deployment script is written and tested; the upload itself takes a few minutes once the token exists.
Phone sign-in | Codes cannot reach Indian numbers | Requires DLT registration with TRAI, or credentials for an SMS account the company already holds. Business registration, not development.
TC-016 | Disease detection reported as showing a rejection | The service was tested directly and responds correctly. Awaiting the exact error text from the testing team.
TC-008 | Username login | The app identifies accounts by email or phone; there is no username system. Replaced with email code sign-in. Awaiting confirmation that this is acceptable.
Both AI models | Further accuracy is limited by photographs, not code | What would help most is real photographs from Indian fields - wheat, rice and cotton for weeds, and specific tomato diseases. Around 50 per category would be worth more than further tuning.
Real-time messaging | Pump control uses a public broker | Anyone who knows a user ID could read sensor data or switch a pump. Needs a private broker before physical hardware is connected.